## Migration Reminders
Category | Reminder / Task | Scheduled Date | Notes / What to Check | Status
GSC | Check first impressions in GSC | 2025-12-25 | GSC → cross-stitch.com → Performance → Impressions (Last 7 days). First signal is Impressions > 0.
GSC / GA | Check migration trend | 2026-01-01 | Compare impressions & sessions vs previous week. Do NOT change redirects/canonicals.
SEO / SEMrush | Evaluate SEMrush & Pinterest status | 2026-01-17 | Compare .net vs .com trends. Decide whether to keep old Pinterest claim.
Email / SES | Decide about retiring .net sending domain | 2026-02-01 | Only if bounce & complaint rates are low and traffic is stable.
Domains | Decide long-term role of cross-stitch-pattern.net | 2026-02-16 | Redirect-only vs secondary brand.
Wrap-up | Final migration review | 2026-03-18 | Redirects, canonicals, sitemap, indexing trend, cleanup decisions.
PDF / Rewrite | Ensure S3 versioning / rollback plan | 2025-12-19 | Preferred: enable versioning on the PDFs bucket. At minimum: keep a full backup copy in a separate bucket/prefix for rollback.
PDF / Rewrite | Create S3 backup copy of all PDFs (rewrite source backup) | 2025-12-19 | Copy current PDF objects from production S3 to a separate bucket/prefix (e.g., pdf-backup/). Do NOT modify originals.
PDF / Rewrite | Create rewrite working copy (temporary) | 2025-12-19 | Copy PDFs to a working prefix/bucket (e.g., pdf-rewrite-temp/). This is the target for test and bulk rewrite runs.
PDF / Rewrite | Define rewrite rules + logging format | 2025-12-19 | Decide replacements (.net → .com). Log per file: key, replaced count, warnings, success/fail.
PDF / Rewrite | Run pilot rewrite on representative sample (20 PDFs) | 2025-12-20 | Pick first/last/random PDFs. Verify: links correct, search works, copy/paste sanity, no visual regression.
PDF / Rewrite | Pilot validation sign-off (go/no-go) | 2025-12-20 | If any gibberish/encoding issues appear, stop and adjust rewrite approach.
PDF / Rewrite | Bulk rewrite PDFs in working copy (idempotent run) | 2025-12-21 | Process all PDFs in pdf-rewrite-temp/. Idempotent: only rewrite when old domain found. Keep failure list for retries.
PDF / Rewrite | Spot-check bulk output (50 random PDFs) | 2025-12-22 | Randomly open 50 rewritten PDFs. Verify links and extractable text. Review failure list.
PDF / Rewrite | Deploy rewritten PDFs by overwriting in place (no emptying) | 2025-12-23 | Copy from pdf-rewrite-temp/ back to the original keys in the production PDFs prefix. Do NOT delete/empty first (atomic per-object replace).
PDF / Rewrite | Keep temp + backup for rollback window, then delete | 2026-01-15 | Keep pdf-backup/ and pdf-rewrite-temp/ for a few weeks. After confidence, delete temp first; keep backup longer if desired.
PDF / Converter | SPEC: Converter CLI + parameters | 2025-12-19 | Desktop C# tool. Inputs: old PDF file(s). Outputs: rewritten PDF(s). Must preserve text extraction/search. Parameters: --input, --output, --baseUrl=https://cross-stitch.com, --dryRun, --logPath, --overwrite.
PDF / Converter | Implement Converter (links-only rewrite, preserve text) | 2025-12-20 | Use iText (your current version). Rewrite only link targets / visible URL text as needed. Avoid reflowing/rewriting unrelated content.
PDF / Converter | Add dry-run mode + detailed logging | 2025-12-20 | Dry-run reports what would change (counts, which URLs). Logging per PDF: file name, replacements, warnings/errors.
PDF / Converter | Add validation checks after conversion | 2025-12-20 | Checks: output opens; contains NO 'cross-stitch-pattern.net'; links point to https://cross-stitch.com; basic text search still works (manual spot-check).
Uploader | Integrate Converter into Uploader pipeline | 2025-12-21 | Uploader flow: generate old-format PDF → run Converter → upload converted PDF to S3. Fail upload if conversion fails. Keep originals locally for troubleshooting.
Uploader | Add UI/flag to enforce conversion on every upload | 2025-12-22 | Default: Converter ON. Add checkbox/status 'Converted: Yes/No' and block upload if 'No'. Optional bypass flag only for already-converted PDFs.
Uploader | Operational checklist: always run Converter before upload | 2025-12-22 | This is the ongoing rule until generator is updated. Add reminder note in the Uploader UI and/or your Excel Status workflow.
PDF / Generator | Update PDF generator to emit cross-stitch.com links natively | 2026-01-05 | Long-term improvement so Converter becomes a safety net, not mandatory. Use env base URL; never emit .net.
PDF / Generator | Safeguard: URL normalization (avoid :443 in generated links) | 2026-01-05 | Ensure generated links are https://cross-stitch.com/... (no :443).

## Converter & Uploader
Category | Reminder / Task | Scheduled Date | Notes / What to Check | Status
PDF / Converter | SPEC: Converter CLI + parameters | 2025-12-19 | Desktop C# tool. Inputs: old PDF file(s). Outputs: rewritten PDF(s). Must preserve text extraction/search. Parameters: --input, --output, --baseUrl=https://cross-stitch.com, --dryRun, --logPath, --overwrite.
PDF / Converter | Implement Converter (links-only rewrite, preserve text) | 2025-12-20 | Use iText (your current version). Rewrite only link targets / visible URL text as needed. Avoid reflowing/rewriting unrelated content.
PDF / Converter | Add dry-run mode + detailed logging | 2025-12-20 | Dry-run reports what would change (counts, which URLs). Logging per PDF: file name, replacements, warnings/errors.
PDF / Converter | Add validation checks after conversion | 2025-12-20 | Checks: output opens; contains NO 'cross-stitch-pattern.net'; links point to https://cross-stitch.com; basic text search still works (manual spot-check).
Uploader | Integrate Converter into Uploader pipeline | 2025-12-21 | Uploader flow: generate old-format PDF → run Converter → upload converted PDF to S3. Fail upload if conversion fails. Keep originals locally for troubleshooting.
Uploader | Add UI/flag to enforce conversion on every upload | 2025-12-22 | Default: Converter ON. Add checkbox/status 'Converted: Yes/No' and block upload if 'No'. Optional bypass flag only for already-converted PDFs.
Uploader | Operational checklist: always run Converter before upload | 2025-12-22 | This is the ongoing rule until generator is updated. Add reminder note in the Uploader UI and/or your Excel Status workflow.