## Migration Reminders
Category | Reminder / Task | Scheduled Date | Notes / What to Check | Status
GSC | Check first impressions in GSC | 2025-12-25 | GSC → cross-stitch.com → Performance → Impressions (Last 7 days). First real signal is Impressions > 0.
GSC / GA | Check migration trend | 2026-01-01 | Compare impressions & sessions vs previous week. Do NOT change redirects or canonicals.
SEO / SEMrush | Evaluate SEMrush & Pinterest status | 2026-01-17 | Compare .net vs .com trends. Decide whether to keep old Pinterest claim.
Domains | Decide long-term role of cross-stitch-pattern.net | 2026-02-16 | Redirect-only vs secondary brand.
Wrap-up | Final migration review | 2026-03-18 | Redirects, canonicals, sitemap, indexing trend, cleanup decisions.
Email / DMARC | Review DMARC aggregate reports (.net) | 2025-12-26 | Expect DKIM=pass, SPF=pass, disposition=none. Single events are normal.
Email / DMARC | Weekly DMARC sanity check | 2026-01-02 | Look for failures or unknown source IPs. p=none is correct during migration.
Email / SES | Confirm SES sending identity stability | 2026-01-05 | Check SES metrics: bounces, complaints, delivery.
Email / SES | Decision: reduce .net sending | 2026-02-01 | Only after traffic and email stabilize.
Email / DMARC | Plan DMARC policy for cross-stitch.com | 2026-02-15 | Draft DMARC for .com (start with p=none). Do NOT enforce yet.
PDF / Rewrite | Ensure S3 versioning or rollback backup | 2025-12-19 | Enable versioning or keep full backup in separate bucket/prefix.
PDF / Rewrite | Create S3 backup copy of all PDFs | 2025-12-19 | Copy production PDFs to pdf-backup/. Originals untouched.
PDF / Rewrite | Create rewrite working copy | 2025-12-19 | Copy PDFs to pdf-rewrite-temp/.
PDF / Rewrite | Define rewrite rules + logging | 2025-12-19 | Replace .net → .com. Log per file.
PDF / Rewrite | Run pilot rewrite on sample | 2025-12-20 | Verify links, search, copy/paste, visuals.
PDF / Rewrite | Bulk rewrite PDFs | 2025-12-21 | Idempotent run in working copy.
PDF / Rewrite | Deploy rewritten PDFs (overwrite in place) | 2025-12-23 | Copy rewritten PDFs to original keys. Do NOT empty bucket.
PDF / Converter | Build Converter CLI (C#) | 2025-12-20 | Params: --input --output --baseUrl=https://cross-stitch.com --dryRun --log.
Uploader | Integrate Converter into Uploader | 2025-12-21 | Generate → convert → upload. Block upload on failure.